## Slide 1
Red | Amber | Green | Total
22 | 3 | 33 | 58
SBD – HCL ALL Towers Weekly Status Report – Project High Level Status | 
Red Projects – Reason | Count
3rd Party Dependency | 4
Scope Change | 1
Technical Issue | 5
Planning/Estimation | 4
Resource Issue | 
Task Delay | 5
HOTS Transition/Process | 2
Funding Issue | 
Refreshed from Teams December 14th @ 8:00am EST
Red | Amber | Green | Total
38% | 5% | 57% | 100%
Summary of ‘Red’ Status Projects | 
Project | Main Issue
PRJ3207 CORP – Project Journey IAP Ph2 Rollout #2 | Sign off from HOTS team is overdue
PRJ3688 Firebird | SBD requested a separate subscription to facilitate an easier separation, first time setups and newly introduced SBD Guidelines and Policies cause significant issues to troubleshoot and resolve in setting up Infra
PRJ3380 Tax/STAT 2020 Greece E-Book | 1 critical issue remains in production, project cannot be closed until resolved.
PRJ3437 QAD/Navision migration to JDE | Missed design tollgate / working with SBD to determine if integration design can be considered complete
PRJ3703 IGA Project – Agora integration | Requirements for the new upcoming 9 applications not finalized (SBD/Accenture)
PRJ3464 GTS CPQ Implementation - Storage | Connection issues impacting the finalization of CPQ
PRJ3795 GTP SAP SHP | Missed Build Exit Milestone
PRJ3797 GTP SAP C11 | Missed Build Start Milestone
PRJ3895 Tax/Stat SAFT Romania | Error while implementing SAP Notes in SHD System
PRJ3631 GRC 12 Application Upgrade | CO#2 in GovernX
PRJ3754 KOFAX Upgrade | Integration challenges – authorization issue, additional configuration is required
PRJ3699 GTS NA Distribution | SBD business delays.
PRJ3469 2021 GES France Base Job Refresh Project | SBD request to extend HC by 1 week
PRJ3916 Treasury Corporate Global Host to Host Release 3 | Infor LX Design: Technical discussions with SBD on clarifying questions are in progress

## Slide 2
SBD – HCL ALL Towers Weekly Status Report – Project High Level Status | 
Refreshed from Teams December 14th @ 8:00am EST
Summary of ‘Red’ Status Projects | 
Project | Main Issue
PRJ3985 Tax Stat Poland ACR report | Report generation is failing due to missing authorization for Object SEF_REPRUN
PRJ3802 2021 GES Netherlands Syntess Rearchitect | One of the servers needs to be exposed to internet and it was not mentioned in BRD
PRJ3930 GES EU EHF Implementation Project | Admin Red
PRJ3723 EANZ Gilwice DC Relocation | Admin Red
PRJ3751 GTS NA Jackson WMS Conversion Legacy to JDA | Admin Red
PRJ3611 GTS NA Millcreek WMS Conversion Legacy to JDA | Admin Red
PRJ3409 GTS Brazil WMS Replacement Phase 1 Gaps with No SAP Impact | Build tollgate approval is pending
PRJ3475 GTS ENG CFTurbo Fan Design, Klocwork..... | Project approved with different applications, 2 new modules in Romax to be Deployed

## Slide 3
Red | Amber | Green | Total
36% | 0% | 64% | 100%
FULL PM / END to END – Project High Level Status | 
SBD Owner – Iain Downton / Steeve Proulx | HCL Owner – Ronnie Brar
Red | Amber | Green | Total
4 | 0 | 7 | 11
Summary of ‘Red’ Status Projects | 
Project | Main Issue
PRJ3985 Tax Stat Poland ACR report | Report generation is failing due to missing authorization for Object SEF_REPRUN
PRJ3802 2021 GES Netherlands Syntess Rearchitect | One of the servers needs to be exposed to internet and it was not mentioned in BRD
PRJ3930 GES EU EHF Implementation Project | Admin Red
PRJ3723 EANZ Gilwice DC Relocation | Admin Red
Red Projects - Reason | Count
3rd Party Dependency | 
Scope Change | 
Technical Issue | 2
Planning/Estimation | 
Resource Issue | 
Task Delay | 2
HOTS Transition/Process | 
Funding Issue | 

## Slide 4
PRJ3464 – GTS-CPQ Implementation-Storage | Status As Of: | 05-Jan-2023
SBD PM: Femi Adeyanju SBD BL: John Marcelo | HCL PM: Miten Shah HCL PD: Ronnie Brar | 
HCL Build Team – Project Change Requests |  |  | 
CO# | Change Request Summary | Impacts | Status
3 | Cloud provide changed to AWS New Design is required | Schedule | Approved
4 | Align time schedule with new delivery dates from 3rd party Configure One | Schedule, Cost | Approved
HCL Weekly Status Report
Status Area | Last Week | Current | Future Trending
HCL Overall Health | Green | Green | Green
Project status is Green. UAT activities are on track
Team Activities:
Support UAT
Agora connection issue is resolved.
Legend: | Red | Amber | Green | Completed
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Dec-2021 | 06-Dec-2021 | Completed
Design Phase End | 19-Jun-2022 | 19-Jun-2022 | Completed
Build Phase Start | 13-Jun-2022 | 13-Jun-2022 | Completed
Build Phase End | 31-Aug-2022 | 31-Aug-2022 | Completed
Systems Integration Testing (SIT) Start | 10-Oct-2022 | 10-Oct-2022 | Completed
Systems Integration Testing (SIT) End | 11-Nov-2022 | 11-Nov-2022 | Completed
User Acceptance Testing (UAT) Start | 14-Nov-2022 | 14-Nov-2022 | Completed
User Acceptance Testing (UAT) End | 3-Feb-2023 | 3-Feb-2023 | 40%
Cutover Start | 27-Feb-2023 | 27-Feb-2023 | Not Started
Cutover End | 6-Mar-2023 | 6-Mar-2023 | Not Started
Go Live | 6-Mar-2023 | 6-Mar-2023 | Not Started
Hypercare Start | 6-Mar-2023 | 6-Mar-2023 | Not Started
Decommissioning Start | 3-Apr-2023 | 3-Apr-2023 | Not Started
Decommission End & Project End | 14-Apr-2023 | 14-Apr-2023 | Not Started
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Due
R | Agora connectivity with CPQ in QA | Agora application cannot connect with CPQ application in QA. While connection worked at one time, environment change and inconsistency across environments has caused this issue. | SBD Agora team is working on syncing environments. After which Agora team can work on resolving connection issue. | SBD Agora lead | Closed

## Slide 5
PRJ3464 – GTS-CPQ Implementation-Storage | Status As Of: | 09-Feb-2023
SBD PM: Femi Adeyanju SBD BL: John Marcelo | HCL PM: Miten Shah HCL PD: Ronnie Brar | 
HCL Build Team – Project Change Requests |  |  | 
CO# | Change Request Summary | Impacts | Status
3 | Cloud provide changed to AWS New Design is required | Schedule | Approved
4 | Align time schedule with new delivery dates from 3rd party Configure One | Schedule, Cost | Approved
HCL Weekly Status Report
Status Area | Last Week | Current | Future Trending
HCL Overall Health | Green | Green | Steady
* Project status is Green from HCL Prospective.
Team Activities:
Support UAT
Legend: | Red | Amber | Green | Completed
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Dec-2021 | 06-Dec-2021 | Completed
Design Phase End | 19-Jun-2022 | 19-Jun-2022 | Completed
Build Phase Start | 13-Jun-2022 | 13-Jun-2022 | Completed
Build Phase End | 31-Aug-2022 | 31-Aug-2022 | Completed
Systems Integration Testing (SIT) Start | 10-Oct-2022 | 10-Oct-2022 | Completed
Systems Integration Testing (SIT) End | 11-Nov-2022 | 11-Nov-2022 | Completed
User Acceptance Testing (UAT) Start | 14-Nov-2022 | 14-Nov-2022 | Completed
User Acceptance Testing (UAT) End | 3-Feb-2023 | 3-Feb-2023 | 90%
Cutover Start | 27-Feb-2023 | 27-Feb-2023 | Not Started
Cutover End | 6-Mar-2023 | 6-Mar-2023 | Not Started
Go Live | 6-Mar-2023 | 6-Mar-2023 | Not Started
Hypercare Start | 6-Mar-2023 | 6-Mar-2023 | Not Started
Decommissioning Start | 3-Apr-2023 | 3-Apr-2023 | Not Started
Decommission End & Project End | 14-Apr-2023 | 14-Apr-2023 | Not Started
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Due

## Slide 6
PRJ3464 – GTS-CPQ Implementation-Storage | Status As Of: | 09-Mar-2023
SBD PM: Femi Adeyanju SBD BL: John Marcelo | HCL PM: Miten Shah HCL PD: Ronnie Brar | 
HCL Build Team – Project Change Requests |  |  | 
CO# | Change Request Summary | Impacts | Status
3 | Cloud provide changed to AWS New Design is required | Schedule | Approved
4 | Align time schedule with new delivery dates from 3rd party Configure One | Schedule, Cost | Approved
HCL Weekly Status Report
Status Area | Last Week | Current | Future Trending
Schedule | Red | Red | Green
Scope | Green | Green | Steady
Cost | Amber | Amber | Green
The Go Live delays are as a result of the time it took the vendor to resolve defects identified during UAT. This has impacted project timeline and possibly cost which will be addressed through a Change Order. There is no change in Scope.​
Team Activities:
Support UAT
Legend: | Red | Amber | Green | Completed
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Dec-2021 | 06-Dec-2021 | Completed
Design Phase End | 19-Jun-2022 | 19-Jun-2022 | Completed
Build Phase Start | 13-Jun-2022 | 13-Jun-2022 | Completed
Build Phase End | 31-Aug-2022 | 31-Aug-2022 | Completed
Systems Integration Testing (SIT) Start | 10-Oct-2022 | 10-Oct-2022 | Completed
Systems Integration Testing (SIT) End | 11-Nov-2022 | 11-Nov-2022 | Completed
User Acceptance Testing (UAT) Start | 14-Nov-2022 | 14-Nov-2022 | Completed
User Acceptance Testing (UAT) End | 3-Feb-2023 | 10-Mar-2023 | 60%
Cutover Start | 27-Feb-2023 | 31-Mar-2023 | Not Started
Cutover End | 6-Mar-2023 | 09-Apr-2023 | Not Started
Go Live | 6-Mar-2023 | 10-Apr-2023 | Not Started
Hypercare Start | 6-Mar-2023 | 10-Apr-2023 | Not Started
Decommissioning Start | 3-Apr-2023 | 17-Apr-2023 | Not Started
Decommission End & Project End | 14-Apr-2023 | 28-Apr-2023 | Not Started
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Due

## Slide 7
PRJ3464 – GTS-CPQ Implementation-Storage | Status As Of: | 06-Apr-2023
SBD PM: Femi Adeyanju SBD BL: John Marcelo | HCL PM: Miten Shah HCL PD: Ronnie Brar | 
HCL Build Team – Project Change Requests |  |  | 
CO# | Change Request Summary | Impacts | Status
3 | Cloud provide changed to AWS New Design is required | Schedule | Approved
4 | Align time schedule with new delivery dates from 3rd party Configure One | Schedule, Cost | Approved
5 | Extend project | Schedule, Cost | In Progress
HCL Weekly Status Report
Status Area | Last Week | Current | Future Trending
Schedule | Red | Red | Green
Scope | Green | Green | Steady
Cost | Amber | Amber | Green
The Go Live delays are as a result of the time it took 3rd party vendor to resolve defects identified during UAT. This has impacted project timeline and possibly cost which will be addressed through a Change Order. There is no change in Scope.​
Note: Commercial coverage ends on 14-Apr-23
Team Activities:
Support UAT
Legend: | Red | Amber | Green | Completed
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Dec-2021 | 06-Dec-2021 | Completed
Design Phase End | 19-Jun-2022 | 19-Jun-2022 | Completed
Build Phase Start | 13-Jun-2022 | 13-Jun-2022 | Completed
Build Phase End | 31-Aug-2022 | 31-Aug-2022 | Completed
Systems Integration Testing (SIT) Start | 10-Oct-2022 | 10-Oct-2022 | Completed
Systems Integration Testing (SIT) End | 11-Nov-2022 | 11-Nov-2022 | Completed
User Acceptance Testing (UAT) Start | 14-Nov-2022 | 14-Nov-2022 | Completed
User Acceptance Testing (UAT) End | 3-Feb-2023 | 28-Apr-2023 | 60%
Cutover Start | 27-Feb-2023 | 1-May-2023 | Not Started
Cutover End | 6-Mar-2023 | 7-May-2023 | Not Started
Go Live | 6-Mar-2023 | 8-May-2023 | Not Started
Hypercare Start | 6-Mar-2023 | 8-May-2023 | Not Started
Decommissioning Start | 3-Apr-2023 | 15-May-2023 | Not Started
Decommission End & Project End | 14-Apr-2023 | 26-May-2023 | Not Started
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Due

## Slide 8
Manufacturing, Supply Chain & Sourcing, Distribution & Logistics - Project High Level Status | 
SBD Owner - Steeve Proulx | HCL Owner – Perry Manous
Red | Amber | Green | Total
3 | 0 | 8 | 11
Red | Amber | Green | Total
27% | 0% | 73% | 100%
Summary of ‘Red’ Status Projects | 
Project | Main Issue
PRJ3751 GTS NA Jackson WMS Conversion Legacy to JDA | Admin Red
PRJ3611 GTS NA Millcreek WMS Conversion Legacy to JDA | Admin Red
PRJ3409 GTS Brazil WMS Replacement Phase 1 Gaps with No SAP Impact | Build tollgate approval is pending
Red Projects - Reason | Count
3rd Party Dependency | 
Scope Change | 
Technical Issue | 
Planning/Estimation | 
Resource Issue | 
Task Delay | 3
HOTS Transition/Process | 
Funding Issue | 

## Slide 9
HCL Build Team – Risks, Issues & Decisions Needed |  |  |  |  | 
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Res Date
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Jun-22 | 06-Jun-22 | Completed
Design Phase End | 15-Jul-22 | 15-Jul-22 | Completed
Build Phase Start | 27 Jun-22 | 27 Jun-22 | Completed
Build Phase End | 23-Sep-22 | 23-Sep-22 | Completed
Stabilize Phase Start | 19-Sep-22 | 19-Sep-22 | Completed
Stabilize Phase End | 6-Jan-23 | 10-Feb-23 | 65%
System Integration Testing-Start | 3-Oct-22 | 3-Oct-22 | Completed
System Integration Testing-End | 11-Nov-22 | 06-Jan-23 | 92%
Deploy Phase Start | 9-Jan-23 | 06-Feb-23 | 
Deploy Phase End | 10-Feb-23 | 10-Mar-23 | 
Business Go Live | 9-Jan-23 | 06-Feb-23 | 
Hypercare Starts | 9-Jan-23 | 06-Feb-23 | 
Hypercare Ends | 10-Feb-23 | 10-Mar-23 | 
PRJ3751 - GTS- NA Jackson WMS Conversion Legacy to JDA | Status As Of: | 05-Jan-2023
SBD PM: Ankit Jain / Rick Boyle SBD BL: Brezhnev Seno | HCL PM: Mohan Menon HCL PD: Richard Brzezicki | 
HCL Build Team – Project Change Requests  Portfolio Review Board (PRB) OR GovernX Work Order |  |  | 
# | Change Request Summary | Impacts | Status
918.1 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.2 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.3 | Change Order for Go Live schedule change | Schedule change | Pending WRA Submission
HCL Weekly Status Report for SBD PMO
Status Area | Last Week | Current | Future Trending
HCL Overall Health | Red | Admin -Red | Steady
Planning /Estimation: STABILIZE (IT)
Project is Administrative RED because Go Live is changed:
The Go Live for the project is replanned from the earlier 09 Jan to 13 Feb 23.
SIT and UAT completion is delayed because of copy back impact. Post copyback SAP TST was built again to restart SIT and UAT.
Path to Green:
Change order created to replan the Go Live for the project from the earlier 09 Jan to 13 Feb 23.
Time used for build completion of the Autosys jobs reset by copyback.
SIT and UAT of the project extended.
Legend: | Red | Amber | Green | Not Started | Completed
R | SIT completion is delayed. | Stabilize end will be likely impacted. | Inventory scenarios initiated from WMS need be successfully completed to end SIT. | Ramya / Brezhnev | 12/30/2022 CLOSED
I | SAP QA systems copyback planned towards end of the year between Dec 10 and 16 is conflicting with the UAT schedule for the project. | The copyback will reset all the transaction data created for SIT before the SIT is complete. | Test data update will be required before SIT is restarted. Copy of all batch jobs is required. These changes will result in schedule and effort impact. | Ramya/ Mohan | 12/23/2022 CLOSED
Notes: Stabilize 17 weeks/ 11weeks ; SIT – 6 weeks/ 1 week

## Slide 10
HCL Build Team – Risks, Issues & Decisions Needed |  |  |  |  | 
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Res Date
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Jun-22 | 06-Jun-22 | Completed
Design Phase End | 15-Jul-22 | 15-Jul-22 | Completed
Build Phase Start | 27 Jun-22 | 27 Jun-22 | Completed
Build Phase End | 23-Sep-22 | 23-Sep-22 | Completed
Stabilize Phase Start | 19-Sep-22 | 19-Sep-22 | Completed
Stabilize Phase End | 03-Feb-23 | 03-Feb-23 | Completed
System Integration Testing-Start | 3-Oct-22 | 3-Oct-22 | Completed
System Integration Testing-End | 06-Jan-23 | 06-Jan-23 | Completed
Deploy Phase Start | 06-Feb-23 | 06-Feb-23 | Completed
Deploy Phase End | 10-Mar-23 | 10-Mar-23 | 20%
Business Go Live | 06-Feb-23 | 06-Feb-23 | Completed
Hypercare Starts | 06-Feb-23 | 06-Feb-23 | Completed
Hypercare Ends | 10-Mar-23 | 10-Mar-23 | 20%
PRJ3751 - GTS- NA Jackson WMS Conversion Legacy to JDA | Status As Of: | 09-Feb-2023
SBD PM: Rick Boyle SBD BL: Brezhnev Seno | HCL PM: Mohan Menon HCL PD: Richard Brzezicki | 
HCL Build Team – Project Change Requests  Portfolio Review Board (PRB) OR GovernX Work Order |  |  | 
# | Change Request Summary | Impacts | Status
918.1 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.2 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.3 | Change Order for Go Live schedule change | Schedule change | APPROVED
HCL Weekly Status Report for SBD PMO
Status Area | Last Week | Current | Future Trending
HCL Overall Health | Green | Green | Steady
Technical and Business Go Live is complete.
Hypercare has started.
Cutover tasks missed out for STO and Induct receiving are being completed.
Hypercare defect monitoring and resolution in progress.
Legend: | Red | Amber | Green | Not Started | Completed
R | Features were deferred till Go live-Reverse Receipt | Operations will be impacted | Needs to be tested and deployed by 2/17 | Brezhnev | Feb 17 2023
R | Picklist job needs to be enabled as a new requirement. | Pack Lists are not dropping from JDA WMS to SAP | Needs to be tested and deployed by 2/17 | Rob/ Brezhnev | Feb 17 2023
Notes: Stabilize 17 weeks/ 13weeks ; SIT – 6 weeks/ 0 week

## Slide 11
HCL Build Team – Risks, Issues & Decisions Needed |  |  |  |  | 
R / I / D | Description | Impact | Mitigation or Actions to Return to Green/Health | Owner | Res Date
Milestones, Phases, Deliverables, etc. | Planned Date | Target Date | RAG & %
Design Phase Start | 06-Jun-22 | 06-Jun-22 | Completed
Design Phase End | 15-Jul-22 | 15-Jul-22 | Completed
Build Phase Start | 27 Jun-22 | 27 Jun-22 | Completed
Build Phase End | 23-Sep-22 | 23-Sep-22 | Completed
Stabilize Phase Start | 19-Sep-22 | 19-Sep-22 | Completed
Stabilize Phase End | 03-Feb-23 | 03-Feb-23 | Completed
System Integration Testing-Start | 3-Oct-22 | 3-Oct-22 | Completed
System Integration Testing-End | 06-Jan-23 | 06-Jan-23 | Completed
Deploy Phase Start | 06-Feb-23 | 06-Feb-23 | Completed
Deploy Phase End | 10-Mar-23 | 10-Mar-23 | 95%
Business Go Live | 06-Feb-23 | 06-Feb-23 | Completed
Hypercare Starts | 06-Feb-23 | 06-Feb-23 | Completed
Hypercare Ends | 10-Mar-23 | 10-Mar-23 | 95%
PRJ3751 - GTS- NA Jackson WMS Conversion Legacy to JDA | Status As Of: | 09-Mar-2023
SBD PM: Rick Boyle SBD BL: Brezhnev Seno | HCL PM: Mohan Menon HCL PD: Richard Brzezicki | 
HCL Build Team – Project Change Requests  Portfolio Review Board (PRB) OR GovernX Work Order |  |  | 
# | Change Request Summary | Impacts | Status
918.1 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.2 | Change Order for Go Live schedule change | Schedule change | APPROVED
918.3 | Change Order for Go Live schedule change | Schedule change | APPROVED
HCL Weekly Status Report for SBD PMO
Technical and Business Go Live is complete.
Hypercare has started.
Cutover tasks missed out for STO and Induct receiving -Completed.
Hypercare defect monitoring and resolution –In Progress.
Legend: | Red | Amber | Green | Not Started | Completed
R | HOTS sign off not received. | HOTS transitions is open | Sign Off has been requested and IT Ops team engaged | IT Ops | 10-Mar -23
Status Area | Last Week | Current | Future Trending
Schedule | Green | Green | Steady
Scope | Green | Green | Steady
Cost | Green | Green | Steady
Notes: Stabilize 17 weeks/ 13weeks ; SIT – 6 weeks/ 0 week